## Schedule
Proposed Schedule
Updated Schedule • Effective upon partial payment received 13 March 2026
📋 If even a partial payment is made today (Friday, 13 March 2026), the updated schedule below will come into effect and all deliverables will be completed by 26 March 2026. Only the remaining features and minor ui corrections of forms discussed earlier, A/B Testing and Devops. (Proposed SRE of 3 months)
📅 DELIVERY SCHEDULE
# | Date | Day | Activity / Milestone | Deliverable | Status
1 | 13 March 2026 | Friday | 🚀 Application goes LIVE on cloud • Partial payment received • Current build deployed to production • All existing features functional | Live Deployment | 🟢 GO LIVE
2 | 14 March 2026 | Saturday | 💬 Discussion Meet #1 • Review all current features • Identify gaps, bugs & amendments • Prioritize remaining work items | Requirements Doc | 📋 REVIEW
3 | 15 March 2026 | Sunday | 💬 Discussion Meet #2 • Finalize amendment list • Agree on scope for completion week • Lock schedule | Final Scope Lock | 📋 REVIEW
4 | 16 March 2026 | Monday | 🔨 Development Sprint — Day 1 • Begin executing agreed amendments • Priority fixes and feature completion | Sprint Progress | 🟡 IN PROGRESS
5 | 17 March 2026 | Tuesday | 🔨 Development Sprint — Day 2 • Continue feature completion • Backend + Frontend integration | Sprint Progress | 🟡 IN PROGRESS
6 | 18 March 2026 | Wednesday | 🔨 Development Sprint — Day 3 • Continue feature completion • Testing & bug fixes | Sprint Progress | 🟡 IN PROGRESS
7 | 19 March 2026 | Thursday | 🔨 Development Sprint — Day 4 • Final feature completion • End-to-end testing • Prepare for final deployment | Sprint Progress- till 26 march | 🟡 IN PROGRESS
8 | 26 March 2026 (8 PM) | Friday | ✅ ALL REMAINING FEATURES COMPLETED • Final deployment to production • Verification & sign-off • Schedule remains undisturbed | ✅ Full Delivery | 🏁 COMPLETE
📊 TIMELINE OVERVIEW
Phase | 13 Fri | 14 Sat | 15 Sun | 16-26 Mon-Thu | 26 Fri
Deployment | 🟢 LIVE
Discussion |  | 💬 Meet 1 | 💬 Meet 2
Development |  |  |  | 🔨 Sprint | ✅ Done
Generated by iKlavya Platform • iklavya.in • Schedule effective upon partial payment confirmation
Document Date: 13 March 2026 • Confidential